## Summary
Step 6 status: tenant-aware authentication and authorization
Change the yellow Status cells on the other sheets; the counts below recalculate.
Status | Guide requirements | Sub-steps and tasks | Tests (count)
Done | 4 | 10 | 5
Ready to build | 3 | 14 | 23
Pending | 0 | 8 | 0
Total | 7 | 32 | 28
Share done | 57.14% | 31.25% | 17.86%
Status meanings
Roadmap steps 6-16: see 'Versions' sheet for progress per version.
Ready to build: full steps and code have been given; not yet built or confirmed by you.
Pending: not started, or deferred to a later step.
How to use
Yellow cells (Status) are the only cells to edit. Pick Done, Ready to build or Pending from the list.
Requirements: the seven points from the Step 6 guide and how well each is covered.
Sub-steps: the work items in order. 'Beyond guide' items come from the security design; 'Before production' items are release blockers.
Tests: expected test counts per class. The total should reach 28 when Step 6 is complete.

## Build Order
Order | Slice | Priority tier | Name | What you get | Tasks | Done | Task IDs | App works when
1 | C1 | P0 Critical | Secure foundation | Sign in, tenant isolation, platform admin creates shops, rate limiting and headers. | 21 | 18 | 6.1, 6.2, 6.3, 6.4, 6.5, 6.6, 6.7, 6.8, 6.9, 6.10, 6.10b, 6.11a, 6.11b, 6.11c, 6.11d, 6.12a, 6.12b, 6.12c, 6.12e, 6.13c, 6.13d | dotnet test passes; login works; platform admin creates a tenant; /health/live shows security headers.
2 | C2 | P0 Critical | Core data model | Branch, categories, products, sales, payments, stock ledger and balance, settings, receipt counters. | 11 | 0 | 7.1, 7.2, 7.3, 7.4, 7.5, 7.6, 7.11, 7.12, 7.13, 7.15, 7.17 | Migration applied; \dt shows the tables; app starts; all tests still pass.
3 | C3 | P0 Critical | Products and opening stock | Create and list products with opening stock; other shops cannot see them. | 4 | 0 | 8.2, 8.3, 8.5, 8.10 | Create a product with opening stock through the API; isolation tests pass.
4 | C4 | P0 Critical | Checkout engine | Price maths, receipt numbers, one-transaction sale, cash and M-Pesa, safe retries. | 11 | 0 | 9.1, 9.3, 9.4, 9.5, 9.7, 9.8, 6.15, 9.19, 11.1, 11.2, 11.3 | POST /sales records a sale, takes stock out, and the same saleId sent twice makes one sale.
5 | C5 | P0 Critical | Sale in the browser | Sign-in screen, product screens, POS screen, payment, receipt. | 10 | 0 | 10.1, 10.2, 10.3, 10.4, 8.7, 8.8, 10.5, 10.6, 10.7, 10.16 | A cashier signs in and completes a cash sale in the browser and prints a receipt.
6 | C6 | P0 Critical | Go live with one shop | Production settings, hosted, migrations, backups, pilot. | 6 | 0 | 15.5, 14.9, 16.1, 16.2, 16.3, 16.5 | Backup restores; one real shop sells for a week with no data loss.
7 | H1 | P1 High | Harden and audit | Audit log, platform tests, hardening tests, real client IP, platform admin MFA, concurrency test. | 9 | 0 | 6.12d, 6.12f, 6.13a, 6.13b, 6.13e, 6.14, 6.16, 6.18, 11.7 | Security events visible in audit table; 28 tests pass; two sales of the last unit cannot both succeed.
8 | H2 | P1 High | Daily shop operations | Categories, barcode scan, settings screen, negative stock rule, sales history, void. | 7 | 0 | 8.1, 8.6, 9.2, 9.6, 9.10, 9.11, 10.8 | Owner can review the day, void a mistake, and scan a barcode.
9 | H3 | P1 High | Stock management | Receive stock, adjust, stock levels and history with screens. | 4 | 0 | 9.13, 9.14, 9.15, 10.10 | Receiving a delivery raises on-hand; adjustments appear in history.
10 | H4 | P1 High | Reports, staff and docs | Daily report, user management, config, README, restricted DB user, compliance review. | 8 | 0 | 9.16, 10.9, 10.11, 10.15, 15.1, 15.2, 16.4, 16.6 | Owner adds a cashier; daily report matches manual total.
11 | H5 | P1 High | Offline foundation | PWA, local database, offline checkout, queue states. | 8 | 0 | 12.1, 12.2, 12.3, 12.4, 12.5, 12.6, 12.10, 7.8 | Sell with the network off; sales wait in the local queue.
12 | H6 | P1 High | Safe sync | Sync endpoint, idempotency, retry, conflicts, pull changes. | 7 | 0 | 13.1, 13.2, 13.3, 13.4, 13.5, 13.7, 13.10 | Reconnect and sync with zero duplicate sales.
13 | H7 | P1 High | Multi-shop onboarding | Tenant onboarding wizard, suspend and reactivate. | 2 | 0 | 14.1, 14.2 | Add a new shop without touching the database.
14 | M1 | P2 Medium | Data and audit polish | Price-change audit, user branches, report indexes, terminals, RLS, commit hygiene. | 8 | 1 | 6.11e, 6.17, 6.21, 7.7, 7.9, 7.14, 7.16, 8.4 | Price edit writes an audit row; cashier limited to assigned branch.
15 | M2 | P2 Medium | Sales extras | Discounts, returns, shifts, category screen, CSV import, password change, toasts. | 7 | 0 | 9.9, 9.12, 9.17, 8.9, 8.11, 10.12, 10.14 | Cashier over discount limit is denied; return restores stock.
16 | M3 | P2 Medium | Quality and demo data | Browser tests, end-to-end test, CI pipeline, demo seed. | 3 | 0 | 11.5, 11.6, 15.4 | CI is green on every push.
17 | M4 | P2 Medium | Offline polish | Stock display rules, offline receipts, local data protection, conflict handling, diagnostics. | 6 | 0 | 12.7, 12.8, 12.9, 13.6, 13.8, 13.9 | Price change while offline is flagged on sync.
18 | M5 | P2 Medium | SaaS operations | Plans, billing status, platform dashboard, monitoring, exports. | 5 | 0 | 14.3, 14.4, 14.6, 14.8, 16.9 | Trial dates and billing status visible per shop.
19 | N1 | P3 Normal | Can wait | Password reset email, refresh cleanup job, frontend unit tests, start script, Swahili UI and similar. | 8 | 0 | 6.20, 8.13, 10.13, 11.4, 14.5, 15.3, 15.6, 16.7 | Added when a customer asks for it.
20 | L1 | P4 Low | Can do without | Product images, customers table, support sessions, suppliers, dedicated installs, multi-terminal reservation. | 6 | 0 | 6.19, 7.10, 8.12, 9.18, 13.11, 14.10 | Only if a customer needs it.
How to use: finish a slice completely (build, tests green, run the app, check the 'App works when' column), commit, then start the next slice.
Never start a slice in a lower tier while a higher tier slice is unfinished, unless a task there is a listed dependency.
Each slice leaves the app runnable. Tests for a feature are added in the slice that builds it.
Some tasks were moved up so no tier is blocked by a lower one: 6.13c, 6.13d, 7.12, 8.5, 15.5 to Critical; 6.13e and 7.8 to High; 7.9 to Medium.
Dependencies were adjusted for the same reason, e.g. 7.17 now covers only the critical tables, and 10.16 needs 10.1-10.7 only.

## Roadmap 6-16
ID | Step | Task | What to build (detail) | Why it matters | Done when (acceptance) | Version | Priority | Layer | Depends on | Effort | Status | My decision / notes | Build slice
6.1 | 6 Auth & authorization | Domain base types | ITenantOwned interface and TenantEntity base class (Id, TenantId, CreatedAtUtc, UpdatedAtUtc). | One shared rule for what 'belongs to a tenant' lets the DbContext enforce isolation generically. | Product and later entities inherit it; project builds. | v1.0 | P0 Critical | Domain |  | S | Done |  | C1
6.2 | 6 Auth & authorization | Permissions and system roles | Permission string catalogue (products.read, products.write, ...), Role and RolePermission entities; roles Owner, Manager, Cashier, StockController. | Permissions, not role names, are checked in code so roles can change without code edits. | Role-permission rows seeded and readable. | v1.0 | P0 Critical | DB | 6.1 | M | Done |  | C1
6.3 | 6 Auth & authorization | Tenant, TenantMembership, Product entities | Tenant(Status, Name), TenantMembership(UserId, TenantId, RoleId, Status), Product with TenantId. | User-to-tenant link with a role is the core of multi-tenancy; a user outside a tenant has no access. | Tables mapped with unique (UserId, TenantId). | v1.0 | P0 Critical | DB | 6.1 | M | Done |  | C1
6.4 | 6 Auth & authorization | Tenant context abstraction and AppUser | ITenantContext (TenantId, UserId) and AppUser : IdentityUser<Guid>. | Keeps tenant lookup out of controllers and allows a test implementation. | Context resolved from claims in API; fake in tests. | v1.0 | P0 Critical | Domain | 6.3 | S | Done |  | C1
6.5 | 6 Auth & authorization | AppDbContext: Identity, query filter, SaveChanges rules | IdentityUserContext, global query filter on ITenantOwned by current TenantId, SaveChanges stamps TenantId and rejects cross-tenant writes. | Even a forgotten Where clause cannot leak another tenant's rows. | Query without tenant returns nothing; write to other tenant throws. | v1.0 | P0 Critical | DB | 6.4 | L | Done |  | C1
6.6 | 6 Auth & authorization | Tenant isolation tests | 5 tests proving read/write isolation at DbContext level against pos_test. | Guide requires tests that prove denial. | 5 tests green. | v1.0 | P0 Critical | Test | 6.5 | M | Done |  | C1
6.7 | 6 Auth & authorization | Migration AddIdentityAndTenancy | Create and apply the first identity/tenant migration to pos_dev. | Schema is repeatable from code. | dotnet ef database update succeeds. | v1.0 | P0 Critical | DB | 6.5 | S | Done |  | C1
6.8 | 6 Auth & authorization | Seed roles, demo tenant and owner | DevSeeder creates roles and permissions, Demo Shop tenant, owner from Seed:OwnerEmail/Seed:OwnerPassword (user-secrets). | Gives a sign-in without hard-coded credentials, per guide. | Owner can sign in; no password in source control. | v1.0 | P0 Critical | API | 6.7 | M | Done |  | C1
6.9 | 6 Auth & authorization | Sign-in, JWT with sub and tid, /me | POST /auth/login validates password, lockout (5 attempts/15 min), issues 15-minute JWT with sub, tid, jti. GET /me returns user, tenant, role, permissions. | Tenant comes from the signed token, never from the browser request. | Login returns token; /me shows correct tenant. | v1.0 | P0 Critical | API | 6.8 | L | Done |  | C1
6.10 | 6 Auth & authorization | Permission policies, default-deny, product endpoints | One authorization policy per permission; PermissionHandler re-checks active membership, tenant status and role permission per request; FallbackPolicy denies by default; other tenants' records return 404. | Revoked users lose access immediately, not at token expiry. | Anonymous call to any non-public endpoint returns 401. | v1.0 | P0 Critical | API | 6.9 | L | Done |  | C1
6.10b | 6 Auth & authorization | ApiFactory, AuthorizationTests, DbCollection | WebApplicationFactory<Program> with Testing environment, pos_test DB, seeded owner, cashier, outsider (no membership), Other Shop; 6 authorization tests. | Proves denial paths end-to-end, a guide requirement. | dotnet test shows 11 passed. | v1.0 | P0 Critical | Test | 6.10 | M | Done |  | C1
6.11a | 6 Auth & authorization | RefreshToken entity, DbContext mapping, migration AddRefreshTokens | Token hash (SHA-256), FamilyId, UsedAt, RevokedAt, ExpiresAt, SessionStartedAt; unique hash index. | Short access tokens need a safe renewal path; hashing means a database leak does not leak sessions. | Migration applied; table exists. | v1.0 | P0 Critical | DB | 6.10 | S | Done |  | C1
6.11b | 6 Auth & authorization | RefreshTokenService and TokenService options | Issue, rotate (atomic consume with ExecuteUpdateAsync), revoke family on reuse, 14-day sliding with 30-day cap, re-check membership and lockout on refresh. | Rotation plus reuse detection stops stolen-token replay. | Reusing an old token revokes the whole family. | v1.0 | P0 Critical | API | 6.11a | L | Done |  | C1
6.11c | 6 Auth & authorization | Auth endpoints: login cookie, /auth/refresh, /auth/logout | HttpOnly, SameSite=Strict, Path=/auth, Secure on HTTPS cookie pos_refresh; CORS AllowCredentials for the frontend origin. | Browser JavaScript can't read the refresh token. | Login sets cookie; refresh returns new access token. | v1.0 | P0 Critical | API | 6.11b | M | Done |  | C1
6.11d | 6 Auth & authorization | RefreshTokenTests (6 tests) | Cookie flags, rotation, reuse detection, logout, suspended membership denied. | Locks behaviour in. | dotnet test shows 17 passed. | v1.0 | P0 Critical | Test | 6.11c | M | Done |  | C1
6.11e | 6 Auth & authorization | Commit 6.11 | git commit 'feat: rotating refresh tokens with reuse detection and logout'. | Checkpoint before platform work. | Clean git status. | v1.0 | P2 Medium | Process | 6.11d | S | Done |  | M1
6.12a | 6 Auth & authorization | AppUser.IsPlatformAdmin flag | Add bool IsPlatformAdmin (default false) to AppUser. Migration comes with 6.13a. | Platform operator is not tied to a tenant role; default false means nobody is promoted by accident. | Project builds. | v1.0 | P0 Critical | DB | 6.11d | S | Done |  | C1
6.12b | 6 Auth & authorization | TokenService: platform token | CreatePlatformToken: scope=platform, no tid, 10-minute lifetime; PlatformTokenMinutes option. | Separate, short-lived token stops tenant tokens and platform tokens being interchangeable. | Decoded token has scope=platform and no tid. | v1.0 | P0 Critical | API | 6.12a | S | Done |  | C1
6.12c | 6 Auth & authorization | Platform admin requirement and handler | Policy platform.admin re-checks IsPlatformAdmin and lockout in database on each call; tenant endpoints reject platform tokens (no tenant). | Revoking the flag takes effect immediately. | Tenant token on /platform returns 403. | v1.0 | P0 Critical | API | 6.12b | M | Done |  | C1
6.12d | 6 Auth & authorization | PlatformAdminSeeder + user-secrets | Create first platform admin from Seed:PlatformAdminEmail/Password (prompted into user-secrets); never promote an existing user. | No hard-coded credentials and no accidental privilege escalation. | Admin exists after first run only in Development. | v1.0 | P1 High | API | 6.12a | S | Pending |  | H1
6.12e | 6 Auth & authorization | Platform endpoints | POST /platform/auth/login, GET/POST /platform/tenants, GET /platform/audit. | Lets you create tenants without SQL; replaces dev-only endpoints. | Platform admin creates a tenant; list shows it. | v1.0 | P0 Critical | API | 6.12c | M | In progress | PlatformEndpoints.cs built; waiting for 23/23 test result | C1
6.12f | 6 Auth & authorization | PlatformAdminTests (6 tests) | Platform admin cannot read tenant products; tenant owner cannot call platform endpoints; revoked flag denied; platform token has no tid. | Proves the separation. | dotnet test shows 23 passed. | v1.0 | P1 High | Test | 6.12e | M | Pending |  | H1
6.13a | 6 Auth & authorization | AuthAuditEvent entity and migration AddPlatformAdminAndAudit | AuthAuditEvents table (no FK to users), DbContext mapping using parameter b; migration also adds IsPlatformAdmin column. | Audit rows must survive user deletion. | Migration applied; flag column and table exist. | v1.0 | P1 High | DB | 6.12a | M | Pending |  | H1
6.13b | 6 Auth & authorization | AuditLog service | Records login success/failure, lockout, refresh reuse, refresh denied; write failure never breaks the request. | Security events are needed to investigate abuse. | Events visible in table after tests. | v1.0 | P1 High | API | 6.13a | M | Pending |  | H1
6.13c | 6 Auth & authorization | Rate limiting on auth endpoints | Fixed window policy 'auth', default 10/min per IP, RateLimit:AuthPermitPerMinute read at request time. | Slows password guessing beyond lockout. | 11th request in a minute returns 429. | v1.0 | P0 Critical | API | 6.12e | S | Pending |  | C1
6.13d | 6 Auth & authorization | Security headers, HSTS, CORS from config, Cache-Control no-store | Replace Program.cs and AuthEndpoints.cs; Cors:Origins list; HSTS outside Development. | Browser-side hardening and safe configuration per environment. | Response headers present on a request. | v1.0 | P0 Critical | API | 6.13c | M | In progress | Program.cs given (CORS from config, headers, HSTS); no AuthEndpoints change needed (no-store is middleware) | C1
6.13e | 6 Auth & authorization | HardeningTests (5 tests) | Audit written, headers, no-store, CORS origins, rate limit. | Locks hardening in. | dotnet test shows 28 passed. | v1.0 | P1 High | Test | 6.13d | M | Pending |  | H1
6.14 | 6 Auth & authorization | Step 6 sign-off | All 28 tests pass; manual check: user can sign in, user without membership cannot query products; commit; git tag step-6-complete. | Guide check for Step 6. | Tag exists. | v1.0 | P1 High | Process | 6.13e | S | Pending |  | H1
6.15 | 6 Auth & authorization | Sales endpoints: no-membership denial test | When /sales exists, add test that a user without membership gets 403 and cannot read sales. | Guide check lists sales explicitly. | Test green (done with 9.19/11.3). | v1.0 | P0 Critical | Test | 9.4 | S | Pending |  | C4
6.16 | 6 Auth & authorization | Forwarded headers for real client IP | UseForwardedHeaders with known proxy; rate limit and audit use real IP. | Behind a proxy every client looks like one IP. | Audit shows client IP. | v1.0 | P1 High | API | 16.2 | S | Pending |  | H1
6.17 | 6 Auth & authorization | Append-only audit permissions | Database role without UPDATE/DELETE on AuthAuditEvents; retention policy documented. | Prevents tampering with logs. | App role cannot delete audit rows. | v1.0 | P2 Medium | Ops | 16.4 | S | Pending |  | M1
6.18 | 6 Auth & authorization | Platform admin MFA (TOTP) | Require TOTP on /platform/auth/login. Required before production. | Platform admin controls every tenant. | Login needs 6-digit code. | v1.2 | P1 High | API | 6.12e | M | Pending |  | H1
6.19 | 6 Auth & authorization | Support sessions | Time-limited, audited, owner-consented access to a tenant's data for support. | Support without sharing passwords. | Every session in audit. | v2.0 | P4 Low | API | 6.18 | L | Pending |  | L1
6.20 | 6 Auth & authorization | Refresh token cleanup job | Scheduled deletion of expired/revoked tokens. | Table grows forever otherwise. | Job removes old rows. | v1.2 | P3 Normal | Ops | 6.11b | S | Pending |  | N1
6.21 | 6 Auth & authorization | PostgreSQL Row-Level Security | Policy using app.tenant_id set per connection; app role must not own tables. | Second isolation layer under the EF filter. | Raw query without tenant returns nothing. | v2.0 | P2 Medium | DB | 7.17 | L | Pending |  | M1
7.1 | 7 Data model | Branch entity + default branch | Branches(Id, TenantId, Name, Code, Address, Phone, IsActive). Seed one 'Main' branch for Demo Shop. Composite unique (TenantId, Code). | Sales and stock are per location; adding it later means rewriting every sales/stock row. | Migration applied; Demo Shop has 1 branch; query filter hides other tenants' branches. | v1.0 | P0 Critical | DB | 6.12e | S | Pending |  | C2
7.2 | 7 Data model | Category entity | Categories(Id, TenantId, Name, ParentId nullable, IsActive). Unique (TenantId, Name). | Products need grouping for the POS screen and reports. | Table exists with tenant filter and unique index. | v1.0 | P0 Critical | DB | 6.12e | S | Pending |  | C2
7.3 | 7 Data model | Extend Product | Add CategoryId, Sku, Barcode, Price (numeric(18,2)), CostPrice, TaxRate (default 0), TrackStock bool, ReorderLevel (numeric(18,3)), UnitOfMeasure (piece, kg, litre, ...; default piece), IsActive, CreatedAtUtc, UpdatedAtUtc, RowVersion. Unique (TenantId, Sku) and (TenantId, Barcode) where not null. Composite FK (TenantId, CategoryId) to Categories. | Composite FK makes cross-tenant category references impossible at database level. Decimal money avoids rounding bugs. A unit of measure is needed because shops sell sugar, rice and oil by weight or volume. | Inserting a product pointing at another tenant's category fails in the database. | v1.0 | P0 Critical | DB | 7.2 | M | Pending |  | C2
7.4 | 7 Data model | Sale and SaleItem entities | Sales(Id uuid client-generated, TenantId, BranchId, TerminalId nullable, CashierUserId, CustomerId nullable, ReceiptNo, Status [Completed/Voided], Subtotal, DiscountTotal, TaxTotal, Total, AmountTendered, ChangeDue, BusinessDate (shop-local day, Africa/Nairobi), CreatedAtUtc, ClientCreatedAtUtc, VoidedAtUtc, VoidReason, VoidedByUserId). SaleItems(Id, TenantId, SaleId, ProductId, ProductNameSnapshot, SkuSnapshot, Quantity numeric(18,3), UnitPrice, LineDiscount, TaxRate, LineTotal). Composite FK (TenantId, SaleId) on SaleItems. | Snapshots keep old receipts correct after a product is renamed or repriced. Client-generated Id is what makes retries and offline sync idempotent. BusinessDate stops a late-night sale landing on the wrong day in reports. | Both tables migrated; unique (TenantId, BranchId, ReceiptNo); a SaleItem pointing at another tenant's sale fails in the database. | v1.0 | P0 Critical | DB | 7.1, 7.3 | M | Pending |  | C2
7.5 | 7 Data model | Payment entity | Payments(Id, TenantId, SaleId, Method [Cash/Mpesa/Card/Other], Amount, Reference nullable, Status [Confirmed], CreatedAtUtc). Composite FK (TenantId, SaleId) to Sales. Unique (TenantId, Reference) where Method = Mpesa and Reference is not null. | Separating payments from sales supports split payments, M-Pesa references and later refunds. | Table exists; method stored as string enum. | v1.0 | P0 Critical | DB | 7.4 | S | Pending |  | C2
7.6 | 7 Data model | StockMovement ledger | StockMovements(Id uuid, TenantId, BranchId, ProductId, QuantityDelta numeric(18,3), Reason [Sale/Receive/Adjust/Return/Void/Opening], SourceType, SourceId, Note, UserId, CreatedAtUtc). Append-only: no update/delete in code. Index (TenantId, BranchId, ProductId). Composite FKs to Branches and Products. | Stock = sum of movements. An auditable ledger beats a mutable quantity column that cannot explain itself. | On-hand quantity query returns correct sum per product/branch. | v1.0 | P0 Critical | DB | 7.1, 7.3 | M | Pending |  | C2
7.7 | 7 Data model | AuditLogs table (business actions) | AuditLogs(Id, TenantId, UserId, Action, EntityType, EntityId, DetailsJson, CreatedAtUtc). Written for price change, void, stock adjustment, user/role change. | Answers 'who changed what' disputes in a shop. Separate from AuthAuditEvents (sign-in events). | Row written when a product price changes. | v1.0 | P2 Medium | DB | 7.3 | S | Pending |  | M1
7.8 | 7 Data model | SyncOperations table (shape only) | SyncOperations(Id uuid, TenantId, DeviceId, Type, PayloadJson, Status [Received/Applied/Rejected], ReceivedAtUtc, AppliedAtUtc, Error). Create now, use in Step 13. | Guide says design idempotency early. Creating the table now avoids a risky late migration. | Table migrated; unused by v1.0 endpoints. | v1.0 | P1 High | DB | 7.4 | S | Pending |  | H5
7.9 | 7 Data model | Terminals table | Terminals(Id, TenantId, BranchId, Name, IsActive). | Needed for receipts, cashier shifts and one-offline-device-per-branch rule. | Table migrated; one default terminal seeded. | v1.1 | P2 Medium | DB | 7.1 | S | Pending |  | M1
7.10 | 7 Data model | Customers table (minimal) | Customers(Id, TenantId, Name, Phone). Optional link on Sale. | Credit sales and loyalty need it; small shops in Mandera often sell on credit. | Optional CustomerId on Sale; filter works. | v1.2 | P4 Low | DB | 7.4 | S | Pending |  | L1
7.11 | 7 Data model | StockLevels balance table | StockLevels(TenantId, BranchId, ProductId, OnHand numeric(18,3), UpdatedAtUtc). Composite primary key (TenantId, BranchId, ProductId). Updated in the same transaction as every StockMovement. Check constraint OnHand >= 0 is optional (see 9.6). | Summing the whole ledger on every sale is slow, and cannot safely stop two cashiers selling the last unit at once. A balance row can be locked and checked; the ledger stays as the audit trail. | Balance equals the sum of movements for every product; test selling the last unit from two requests (11.7). | v1.0 | P0 Critical | DB | 7.6 | M | Pending |  | C2
7.12 | 7 Data model | TenantSettings table | TenantSettings(TenantId PK, CurrencyCode default KES, TaxInclusive, DefaultTaxRate, BusinessName, Address, Phone, ReceiptFooter, TaxPIN nullable, AllowNegativeStock default false). One row per tenant; Demo Shop seeded. | Totals, receipts and the negative-stock rule depend on per-shop settings. Moved here from 9.2 so the checkout tables and settings are created in one migration. | Demo Shop has one settings row; query filter hides other tenants' settings. | v1.0 | P0 Critical | DB | 7.1 | S | Pending |  | C2
7.13 | 7 Data model | ReceiptCounters table | ReceiptCounters(TenantId, BranchId, NextNumber, Prefix). Composite primary key (TenantId, BranchId). Seeded for the Main branch. | Gap-free, readable receipt numbers need a row that can be locked inside the sale transaction; two simultaneous sales must never share a number (9.3). | Table exists; Main branch counter seeded at 1. | v1.0 | P0 Critical | DB | 7.1 | S | Pending |  | C2
7.14 | 7 Data model | User to branch assignment | UserBranches(TenantId, UserId, BranchId). Composite primary key; composite FKs to TenantMemberships and Branches. Owner sees all branches; others only assigned ones. | Without it, any cashier of the tenant can sell at or read any branch. | Cashier assigned to Main only; a request for another branch is denied (tested in 9.4). | v1.0 | P2 Medium | DB | 7.1 | S | Pending |  | M1
7.15 | 7 Data model | Tenant keys and audit columns on every new table | Every new table carries TenantId and a composite FK to its parent (TenantId, ParentId), not just ParentId. All business tables get CreatedAtUtc and CreatedByUserId; master data also UpdatedAtUtc. Money numeric(18,2), quantities numeric(18,3), times in UTC. | A payment or sale line must not be able to point at another shop's sale or product even through a coding mistake. Consistent columns make audit and reports simpler. | Review of the generated SQL (7.17) shows no table with a single-column FK to a tenant-owned parent. | v1.0 | P0 Critical | DB | 7.4, 7.5, 7.6 | S | Pending |  | C2
7.16 | 7 Data model | Report indexes and demo seed data | Index Sales (TenantId, BranchId, BusinessDate) and (TenantId, BranchId, CreatedAtUtc); Payments (TenantId, SaleId); StockMovements (TenantId, ProductId, CreatedAtUtc). Seed for Demo Shop: Main branch, default terminal, 'General' category, 5 sample products with opening stock. | History and report screens always filter by tenant, branch and date, so those indexes are needed from the start. Sample data lets the first screens show something. | EXPLAIN on the daily-sales query uses the index; Demo Shop lists sample products. | v1.0 | P2 Medium | DB | 7.4, 7.6 | S | Pending | Own migration when built. | M1
7.17 | 7 Data model | Migration AddCoreDataModel + review SQL | One migration (AddCoreDataModel) for the critical tables 7.1-7.6, 7.11-7.13 and 7.15. Review the generated SQL before applying (dotnet ef migrations script): numeric not double, composite FKs and unique indexes present, no single-column FK to a tenant-owned parent. Tables from 7.7-7.10, 7.14 and 7.16 get their own small migration when their slice is built. | Reading the SQL catches wrong types (e.g. double instead of numeric) before data exists. | dotnet ef database update succeeds; \dt in psql shows the critical tables; app still starts and all tests pass. | v1.0 | P0 Critical | DB | 7.1-7.6, 7.11, 7.12, 7.13, 7.15 | S | Pending |  | C2
8.1 | 8 Products & categories | Category API | GET /categories, POST, PUT /{id}, DELETE (soft: IsActive=false). Permissions: products.read / products.write. | Category must exist before products can be organised. | All endpoints return 401/403/404 correctly; tenant filter applied. | v1.0 | P1 High | API | 7.2 | M | Pending |  | H2
8.2 | 8 Products & categories | Product API: list with paging, search, filter | GET /products?search=&categoryId=&page=&pageSize=&active= returning {items,total}. Search by name, SKU, barcode (case-insensitive, indexed). Max pageSize 100. | Never load every product; shops can have thousands of SKUs. | Searching 'sug' returns sugar; page 2 returns next items. | v1.0 | P0 Critical | API | 7.3 | M | Pending |  | C3
8.3 | 8 Products & categories | Product API: create, update, deactivate | POST/PUT/DELETE(soft). Server validation: name required, price >= 0, 2 decimals, SKU/barcode unique per tenant, category belongs to tenant, concurrency via RowVersion (409 on conflict). Return ProblemDetails with field errors. | Server is the only trusted validator; frontend rules are convenience. | Duplicate SKU returns 409/400 with clear message; other tenant's category ID returns 404. | v1.0 | P0 Critical | API | 8.2 | M | Pending |  | C3
8.4 | 8 Products & categories | Price change audit | Write AuditLogs row (old price, new price, user) when price changes. | Detects staff price tampering. | Audit row appears after PUT with new price. | v1.0 | P2 Medium | API | 7.7, 8.3 | S | Pending |  | M1
8.5 | 8 Products & categories | Opening stock on product create | Optional OpeningQuantity creates a StockMovement(Reason=Opening) for the user's branch. | Lets owner load existing shop stock without a separate step. | On-hand equals opening quantity. | v1.0 | P0 Critical | API | 7.6, 8.3 | S | Pending |  | C3
8.6 | 8 Products & categories | Barcode lookup endpoint | GET /products/by-barcode/{code}. | Barcode scanner types digits + Enter; need instant exact lookup. | Returns product or 404 in under 100 ms locally. | v1.0 | P1 High | API | 8.3 | S | Pending |  | H2
8.7 | 8 Products & categories | Frontend: product list page | Table with search box (debounced), category filter, pagination, active toggle, loading/empty/error states, low-stock badge. | Daily-use screen for owner/stock controller. | Refresh page keeps data from DB; empty state shows 'Add your first product'. | v1.0 | P0 Critical | Frontend | 8.2 | M | Pending |  | C5
8.8 | 8 Products & categories | Frontend: product form | Create/edit form with inline validation errors from server, price formatting (KES), category picker, save/cancel, prevents double submit. | Reduces data-entry errors. | Added product visible after refresh; validation message shown for duplicate SKU. | v1.0 | P0 Critical | Frontend | 8.3 | M | Pending |  | C5
8.9 | 8 Products & categories | Frontend: category management | Simple list + add/rename/deactivate dialog. | Needed for the POS category filter. | Category appears in product form dropdown. | v1.0 | P2 Medium | Frontend | 8.1 | S | Pending |  | M2
8.10 | 8 Products & categories | Tenant isolation tests for products/categories | Tests: tenant A cannot get, update, delete or list tenant B's products/categories; cashier cannot POST. | Guide completion check for Step 8. | Tests green and included in dotnet test. | v1.0 | P0 Critical | Test | 8.3 | M | Pending |  | C3
8.11 | 8 Products & categories | Bulk import products from CSV | Upload CSV (name, sku, barcode, price, category, opening qty), validate rows, report errors per line, insert in one transaction. | Real shops have hundreds of items; typing them is the biggest adoption barrier. | Import of 200 rows works; bad rows reported without partial insert. | v1.1 | P2 Medium | API+Frontend | 8.3 | L | Pending |  | M2
8.12 | 8 Products & categories | Product images | Optional image upload (size limit, type check) stored on disk/object storage. | Helps cashier recognise items; not required for sale. | Image shows in POS tile. | v2.0 | P4 Low | API+Frontend | 8.7 | M | Pending |  | L1
8.13 | 8 Products & categories | Product variants / units of measure | Variants (size/colour) and unit conversions (carton to piece). | Common in wholesale; adds complexity to stock. | Sell by piece, receive by carton. | v2.0 | P3 Normal | DB+API | 8.3 | L | Pending |  | N1
9.1 | 9 Checkout & stock ledger | Pricing and rounding rules (domain class) | Pure C# class SaleCalculator: line total = round(qty*price - discount, 2, MidpointRounding.AwayFromZero); tax handling (inclusive/exclusive setting per tenant); totals from lines. No EF or HTTP inside. | Money logic must be unit-testable and identical everywhere. | Unit tests for rounding, discount, tax, zero qty pass. | v1.0 | P0 Critical | Domain | 7.4 | M | Pending |  | C4
9.2 | 9 Checkout & stock ledger | Tenant settings (currency, tax, receipt header) | TenantSettings: CurrencyCode (KES), TaxInclusive, DefaultTaxRate, BusinessName, Address, Phone, receipt footer, TaxPIN optional. | Receipts and totals depend on them. | GET/PUT /settings (owner only). | v1.0 | P1 High | DB+API | 7.1 | S | Pending | Table is created in 7.12; this step adds the GET/PUT endpoints. | H2
9.3 | 9 Checkout & stock ledger | Receipt numbering | Per branch sequential ReceiptNo generated server-side in the transaction (e.g. MAIN-000123) using a counter row with lock. | Shops need readable, gap-free receipt numbers; UUID is not human friendly. | Two concurrent sales never share a number. | v1.0 | P0 Critical | API | 7.4 | M | Pending | Counter table is created in 7.13; this step adds the numbering logic. | C4
9.4 | 9 Checkout & stock ledger | POST /sales (checkout) in one transaction | Request: saleId (client UUID), branchId, items[{productId, quantity}], payments[{method, amount, reference}]. Server re-reads prices from DB, validates product active/belongs to tenant, qty > 0, branch belongs to user's membership, payment >= total. Creates Sale, SaleItems, Payments, StockMovements(-qty) atomically. | Never trust browser totals. A single transaction means no half-saved sale. | Forced failure mid-way leaves zero rows in all tables. | v1.0 | P0 Critical | API | 9.1, 9.3, 7.4-7.6, 7.11, 7.13 | L | Pending | No stock check until 9.6 (negative stock policy); stock ledger and StockLevels are updated in the same transaction. | C4
9.5 | 9 Checkout & stock ledger | Idempotent sale submission | If saleId already exists for tenant, return the stored sale (200) rather than creating another. Unique index on (TenantId, Id). | Network retries and later offline sync must not duplicate sales. | Posting same saleId twice yields one sale and one set of stock movements. | v1.0 | P0 Critical | API | 9.4 | S | Pending |  | C4
9.6 | 9 Checkout & stock ledger | Negative stock policy | Tenant setting AllowNegativeStock (default false). If false and on-hand < qty, return 409 listing products. Use row lock / serializable check on product stock during checkout. | Prevents overselling; shop decides strictness. | Selling more than on-hand is rejected when setting is off. | v1.0 | P1 High | API | 9.4 | M | Pending |  | H2
9.7 | 9 Checkout & stock ledger | Cash payment, change due | Cash tendered vs total; change = tendered - total, stored on Payment. | Cashier needs change figure on screen and receipt. | Receipt shows tendered and change. | v1.0 | P0 Critical | API | 9.4 | S | Pending |  | C4
9.8 | 9 Checkout & stock ledger | M-Pesa (manual reference) and other payment methods | Accept method=Mpesa with transaction code reference (validated format, unique per tenant), split payments (cash + M-Pesa). No live API call in v1.0. | Most Kenyan retail takes M-Pesa; recording the code gives reconciliation without integration risk. | Sale with Mpesa reference saved; duplicate reference rejected. | v1.0 | P0 Critical | API | 9.4 | M | Pending |  | C4
9.9 | 9 Checkout & stock ledger | Discounts | Per-line and per-sale discount (amount or %), permission sales.discount, max % per role, audit entry. | Common POS need; permission-gated to prevent abuse. | Cashier over limit is denied; manager allowed. | v1.1 | P2 Medium | API | 9.4 | M | Pending |  | M2
9.10 | 9 Checkout & stock ledger | Sales history API | GET /sales?from=&to=&branchId=&cashierId=&page=; GET /sales/{id} with items and payments. Cashier sees only own sales unless permission sales.read.all. | Owner reviews the day; guide requires history. | Sale appears once; other tenant's sale is 404. | v1.0 | P1 High | API | 9.4 | M | Pending |  | H2
9.11 | 9 Checkout & stock ledger | Void sale | POST /sales/{id}/void with reason; permission sales.void; sets Status=Voided and adds reversing StockMovements(+qty, Reason=Void); never deletes rows. | Mistakes happen; ledger must stay traceable. | Stock restored; audit row; second void rejected. | v1.0 | P1 High | API | 9.10 | M | Pending |  | H2
9.12 | 9 Checkout & stock ledger | Returns / refunds | Return items against a sale: reversing stock movements, refund payment record, limit to sold quantity. | Customers return goods; needed within weeks of real use. | Cannot return more than sold. | v1.1 | P2 Medium | API | 9.10 | L | Pending |  | M2
9.13 | 9 Checkout & stock ledger | Stock receiving (purchases-lite) | POST /stock/receive {branchId, items[{productId, qty, unitCost}], supplierName?, note} creates StockMovements(Receive) and updates cost price optionally. Permission stock.write. | Without receiving, stock only goes down and shows wrong numbers. | On-hand increases; audit written. | v1.0 | P1 High | API | 7.6 | M | Pending |  | H3
9.14 | 9 Checkout & stock ledger | Stock adjustment (count correction, damage) | POST /stock/adjust with reason (Damage, Expired, CountCorrection) and mandatory note. | Physical stock rarely matches system. | Adjustment row visible in movement history. | v1.0 | P1 High | API | 7.6 | S | Pending |  | H3
9.15 | 9 Checkout & stock ledger | Stock levels and movement history API | GET /stock?branchId= (on-hand, reorder flag), GET /stock/{productId}/movements. | Stock controller needs to see what is low and why. | Totals match sum of ledger. | v1.0 | P1 High | API | 7.6 | M | Pending |  | H3
9.16 | 9 Checkout & stock ledger | Reports: daily totals | GET /reports/daily?date=&branchId= returning sales count, gross, discounts, tax, totals by payment method, voids, top 10 products. | Guide requires a simple daily report; shop closes the day with it. | Numbers match manual sum of sales. | v1.0 | P1 High | API | 9.10 | M | Pending |  | H4
9.17 | 9 Checkout & stock ledger | Cashier shift / cash drawer (open, close, variance) | Open shift with float, close with counted cash; variance = counted - (float + cash sales). | Controls theft and till shortages. | Variance computed and stored. | v1.2 | P2 Medium | API+Frontend | 9.10 | L | Pending |  | M2
9.18 | 9 Checkout & stock ledger | Suppliers and purchase orders | Suppliers, POs, receive against PO, supplier payments. | Guide defers supplier workflows; keep after core sale. | PO received creates stock movements. | v2.0 | P4 Low | DB+API | 9.13 | L | Pending |  | L1
9.19 | 9 Checkout & stock ledger | Domain/unit + integration tests for checkout | Unit tests for calculator; API tests for atomic rollback, idempotency, negative stock, void, tenant isolation on sales. | Money code must have the densest tests. | All pass in CI. | v1.0 | P0 Critical | Test | 9.1, 9.3-9.5, 9.7, 9.8 | L | Pending |  | C4
10.1 | 10 End-to-end workflow | Frontend app shell, routing, auth guard | React Router, layout with sidebar, role-based menu items, redirect to sign-in when 401. | Gives structure for all screens. | Unauthenticated user sees sign-in only. | v1.0 | P0 Critical | Frontend | 6.11c | M | Pending |  | C5
10.2 | 10 End-to-end workflow | Sign-in screen + session handling | Form posts /auth/login; access token kept in memory; silent refresh via cookie on page load and on 401; logout calls /auth/logout. | Matches Step 6.11 design; avoids tokens in localStorage. | Refresh the page and stay signed in; logout clears session. | v1.0 | P0 Critical | Frontend | 6.11c | M | Pending |  | C5
10.3 | 10 End-to-end workflow | API client wrapper | Single fetch wrapper adding Authorization, handling 401 refresh retry once, ProblemDetails parsing, timeouts, offline/unavailable message. Base URL from VITE_API_URL. | One place for error handling and config. | Stopping the API shows a friendly message. | v1.0 | P0 Critical | Frontend | 10.2 | M | Pending |  | C5
10.4 | 10 End-to-end workflow | Load /me, tenant, branch selection | After login fetch user, tenant name, permissions, allowed branches; store selected branch (persist per device). | POS must know the branch before selling. | Header shows shop and branch names. | v1.0 | P0 Critical | Frontend+API | 10.2, 7.1 | M | Pending |  | C5
10.5 | 10 End-to-end workflow | POS sale screen | Product search/barcode input (Enter adds item), category tiles, cart with +/- quantity and remove, live totals, hold/clear cart, keyboard shortcuts. | Core cashier workflow; speed matters. | Cashier can build a 5-item cart in under 30 seconds. | v1.0 | P0 Critical | Frontend | 10.3 | L | Pending | Search by name first; barcode scan (8.6) is added in slice H2. | C5
10.6 | 10 End-to-end workflow | Payment dialog | Cash/M-Pesa/split, tendered amount, change due, reference input; generates saleId UUID before sending; disables button while submitting. | Client UUID + disabled button prevents duplicates. | Completed sale appears once in history. | v1.0 | P0 Critical | Frontend | 9.4, 10.5 | M | Pending |  | C5
10.7 | 10 End-to-end workflow | Receipt view and print | Receipt component (shop header, items, totals, payment, receipt no, cashier, footer), browser print CSS for 58/80 mm thermal paper, reprint from history. | Customers expect a receipt. | Print preview fits 80 mm width. | v1.0 | P0 Critical | Frontend | 10.6 | M | Pending | Uses default KES and generic header until 9.2 (settings endpoints) is built. | C5
10.8 | 10 End-to-end workflow | Sales history screen | Date range, cashier filter, list with totals, detail drawer, void button (permission-gated). | Owner/manager review. | Void changes status and stock. | v1.0 | P1 High | Frontend | 9.10 | M | Pending |  | H2
10.9 | 10 End-to-end workflow | Daily report screen | Date picker, totals cards, payment method breakdown, top products, print. | Closing the day. | Matches API report. | v1.0 | P1 High | Frontend | 9.16 | M | Pending |  | H4
10.10 | 10 End-to-end workflow | Stock screens | Stock levels with low-stock filter, receive stock form, adjustment form, movement history. | Stock controller workflow. | Receiving updates on-hand immediately. | v1.0 | P1 High | Frontend | 9.13-9.15 | L | Pending |  | H3
10.11 | 10 End-to-end workflow | User management (owner) | Owner invites/creates staff user in own tenant, assigns role, deactivates membership, resets password (temporary password forced change). API: /users, /users/{id}/role, /users/{id}/deactivate. | Owner cannot onboard cashiers without it; today only seeded users exist. | New cashier can sign in; deactivated cashier is denied at next request. | v1.0 | P1 High | API+Frontend | 6.14 | L | Pending |  | H4
10.12 | 10 End-to-end workflow | Change own password / forced change | POST /auth/change-password; revoke all refresh tokens afterwards. | Basic account hygiene. | Old password stops working. | v1.0 | P2 Medium | API+Frontend | 6.11c | S | Pending |  | M2
10.13 | 10 End-to-end workflow | Password reset by email | Reset link via email provider, token expiry, rate limit. | Needs email infrastructure; owner can reset staff passwords in v1.0. | Reset email arrives and works once. | v1.2 | P3 Normal | API | 10.11 | M | Pending |  | N1
10.14 | 10 End-to-end workflow | Global error and empty states, toasts | Consistent loading spinners, error boundary, toast messages. | Usability baseline. | No unhandled blank screens. | v1.0 | P2 Medium | Frontend | 10.1 | S | Pending |  | M2
10.15 | 10 End-to-end workflow | Environment config and narrow CORS | Cors:Origins set to the frontend URL only; VITE_API_URL in .env files; no secrets in frontend. | Guide requirement. | Request from another origin is blocked. | v1.0 | P1 High | Config | 6.13d | S | Pending |  | H4
10.16 | 10 End-to-end workflow | Milestone check: complete one sale in browser | Manual script: sign in, add product, sell it, view receipt, see sale in history and row in PostgreSQL. | Guide milestone for Step 10. | Checklist signed off. | v1.0 | P0 Critical | Test | 10.1-10.7 | S | Pending |  | C5
11.1 | 11 Tests | Domain unit tests (xUnit) | Calculator, discount, tax, rounding, stock rules. | Pure logic is cheapest to test. | Green with at least 25 cases. | v1.0 | P0 Critical | Test | 9.1 | M | Pending |  | C4
11.2 | 11 Tests | API integration tests on pos_test database | WebApplicationFactory; tests for product CRUD, checkout atomicity, idempotency, validation, auth and permissions. | Catches regressions across layers. | Suite runs from dotnet test. | v1.0 | P0 Critical | Test | 9.19 | L | Pending |  | C4
11.3 | 11 Tests | Tenant isolation test matrix | Generated tests across every tenant-owned endpoint: A cannot list/get/update/delete B's records; user without membership gets 403. | Guide's non-negotiable. | Every endpoint appears in the matrix. | v1.0 | P0 Critical | Test | 8.10, 9.4 | L | Pending |  | C4
11.4 | 11 Tests | Frontend tests (Vitest + Testing Library) | Product form validation, cart totals, error display, auth guard. | Prevents UI regressions in cashier flow. | npm test passes. | v1.0 | P3 Normal | Test | 10.5 | M | Pending |  | N1
11.5 | 11 Tests | End-to-end test (Playwright) | Sign in, add product, checkout, verify history. Runs against test DB. | Proves the whole stack. | Test passes headless locally. | v1.0 | P2 Medium | Test | 10.16 | L | Pending |  | M3
11.6 | 11 Tests | CI pipeline (GitHub Actions) | On push: dotnet build/test with PostgreSQL service, npm ci/lint/test/build. | Guide: tests in the normal build. | Green check on commits. | v1.0 | P2 Medium | Ops | 11.2 | M | Pending |  | M3
11.7 | 11 Tests | Concurrency test: two sales of last unit | Two parallel checkout requests for stock of 1: one succeeds, one gets 409. | Foreshadows offline conflicts. | Test deterministic. | v1.0 | P1 High | Test | 9.6 | M | Pending |  | H1
12.1 | 12 PWA & offline | PWA manifest + service worker (vite-plugin-pwa) | Manifest, icons, installable, precache app shell only; update prompt on new version. | Required for offline start and install on shop PC/phone. | Lighthouse installable check passes. | v1.1 | P1 High | Frontend | 10.16 | M | Pending |  | H5
12.2 | 12 PWA & offline | Dexie database schema | Tables: products, categories, stockSnapshot, pendingSales, syncQueue, meta (lastPullAt, deviceId). Schema versioning. | Durable local storage in IndexedDB. | Data survives browser restart. | v1.1 | P1 High | Frontend | 12.1 | M | Pending |  | H5
12.3 | 12 PWA & offline | Local product cache + refresh | Pull products/categories/prices after login and periodically; search runs against IndexedDB when offline. | Cashier needs catalogue offline. | Search works with network disabled. | v1.1 | P1 High | Frontend | 12.2, 13.7 | M | Pending |  | H5
12.4 | 12 PWA & offline | Offline checkout | Same cart UI; builds sale with client UUID and local receipt no (device prefix), writes sale + payment + local stock movement + queue entry in ONE Dexie transaction. | Atomic local save avoids lost sales. | Offline sale persists after closing browser. | v1.1 | P1 High | Frontend | 12.2, 9.4 | L | Pending |  | H5
12.5 | 12 PWA & offline | Online/offline indicator and queue states | Badge online/offline; per-sale state pending/syncing/synced/failed; count of pending items. | Cashier must know what is unsynced. | Indicator changes on network toggle. | v1.1 | P1 High | Frontend | 12.4 | S | Pending |  | H5
12.6 | 12 PWA & offline | Offline authentication rules | Allow already signed-in session to continue offline for limited hours; require online sign-in for new devices; never cache passwords. | Balance usability and security. | Documented and tested behaviour on expiry. | v1.1 | P1 High | Frontend+API | 12.1 | M | Pending |  | H5
12.7 | 12 PWA & offline | Locally calculated vs server-confirmed stock | Show local estimate with label; store lastConfirmedStock and pending deltas. | Offline stock is not authoritative. | UI shows 'unconfirmed' tag offline. | v1.1 | P2 Medium | Frontend | 12.4 | M | Pending |  | M4
12.8 | 12 PWA & offline | Offline receipts and local sales list | View/print receipts for pending sales; list of today's offline sales. | Customers still need receipts. | Receipt prints offline. | v1.1 | P2 Medium | Frontend | 12.4 | S | Pending |  | M4
12.9 | 12 PWA & offline | Local data protection | Clear local data on logout; warn about shared PCs; optional encryption of queue. | Offline data contains business data. | Logout empties Dexie tables. | v1.1 | P2 Medium | Frontend | 12.2 | S | Pending |  | M4
12.10 | 12 PWA & offline | Offline test pass | Manual script: go offline, refresh, search, sell, close browser, reopen, still there. | Guide completion check. | Checklist signed off. | v1.1 | P1 High | Test | 12.4 | S | Pending |  | H5
13.1 | 13 Synchronization | Sync endpoint POST /sync/sales | Accepts batch of sales with operationId and deviceId; validates each as in 9.4; returns per-item result Applied/Duplicate/Rejected(reason). | Single entry for queued sales. | Batch of 3 returns 3 results. | v1.1 | P1 High | API | 9.5, 7.8 | L | Pending |  | H6
13.2 | 13 Synchronization | Idempotency via SyncOperations | Record operationId before applying; replays return original result; unique (TenantId, OperationId). | Retries must never duplicate. | Same batch sent twice creates one set of rows. | v1.1 | P1 High | API | 13.1 | M | Pending |  | H6
13.3 | 13 Synchronization | Client sync engine | Ordered queue processing (oldest first), exponential backoff, only one sync at a time, resumes on reconnect and app start, handles 401 by refreshing token. | Reliable delivery. | Kill network mid-sync; resumes cleanly. | v1.1 | P1 High | Frontend | 13.1 | L | Pending |  | H6
13.4 | 13 Synchronization | Failure handling and manual retry | Failed items kept with error message, 'Retry' and 'Needs attention' list for manager; no silent drop. | Guide: retry and recovery. | Rejected sale visible with reason. | v1.1 | P1 High | Frontend | 13.3 | M | Pending |  | H6
13.5 | 13 Synchronization | Conflict policy: insufficient stock on sync | Default: accept the sale (goods already handed over), record stock as negative and flag 'Stock conflict' for manager review. Never overwrite silently. | A completed sale cannot be undone; stock needs reconciling. | Flag appears in manager inbox. | v1.1 | P1 High | API+Frontend | 13.1 | M | Pending |  | H6
13.6 | 13 Synchronization | Price/product changed while offline | Sale keeps the price the customer was charged (snapshot); server logs difference vs current price. | Customer paid agreed price. | Mismatch recorded not rejected. | v1.1 | P2 Medium | API | 13.1 | S | Pending |  | M4
13.7 | 13 Synchronization | Pull changes endpoint | GET /sync/changes?since=cursor returns products, categories, prices, stock for branch; cursor-based using UpdatedAt/version. | Keeps local cache fresh. | Edited product appears on device after pull. | v1.1 | P1 High | API | 13.1 | M | Pending |  | H6
13.8 | 13 Synchronization | Sync logging and diagnostics screen | Server logs operationId, device, outcome; screen shows last sync time, pending count, errors; export diagnostics. | Troubleshooting in the field. | Support can see why a sale failed. | v1.1 | P2 Medium | API+Frontend | 13.3 | M | Pending |  | M4
13.9 | 13 Synchronization | One offline terminal per branch rule | Register device; server rejects offline sync from second unregistered terminal or warns. | Guide recommended first-release limit. | Second device flagged. | v1.1 | P2 Medium | API | 7.9 | M | Pending |  | M4
13.10 | 13 Synchronization | Sync tests | Interrupted connection, duplicate batch, app restart mid-sync, two devices selling last unit, clock skew. | Guide step 13 test list. | All scenarios automated or scripted. | v1.1 | P1 High | Test | 13.1-13.5 | L | Pending |  | H6
13.11 | 13 Synchronization | Multi-terminal offline stock reservation | Allocate stock quotas per terminal or use conflict resolution UI. | Guide: only after single-device is stable. | Two offline terminals reconcile. | v2.0 | P4 Low | API+Frontend | 13.10 | L | Pending |  | L1
14.1 | 14 SaaS management | Platform: tenant onboarding wizard | Platform admin creates tenant + owner + default branch + default roles in one transaction (builds on 6.12e POST /platform/tenants). Returns one-time temporary password. | How you add customers without SQL. | New shop can sign in right away. | v1.2 | P1 High | API+Frontend | 6.12e | M | Pending |  | H7
14.2 | 14 SaaS management | Tenant suspend/reactivate | Status Suspended blocks all tenant sign-ins and API calls with clear message; platform audit entry. | Non-payment or abuse handling. | Suspended tenant gets 403 on next request. | v1.2 | P1 High | API | 6.12e | S | Pending |  | H7
14.3 | 14 SaaS management | Plans, trial dates, entitlements | Plans(Name, MaxBranches, MaxUsers, MaxProducts, Features), Subscriptions(TenantId, PlanId, Status, TrialEndsAt, CurrentPeriodEnd). Enforced in API with clear error. | Limits and trial control revenue. | Creating user over the limit is rejected. | v1.2 | P2 Medium | DB+API | 14.1 | L | Pending |  | M5
14.4 | 14 SaaS management | Manual billing status | Platform admin marks paid until date (no payment provider yet); expired subscription -> read-only grace then suspend. | Guide: don't build billing before core; manual works for first customers. | Expired tenant becomes read-only. | v1.2 | P2 Medium | API | 14.3 | M | Pending |  | M5
14.5 | 14 SaaS management | Billing provider integration (separate module) | M-Pesa Daraja/Stripe webhooks verified server-side; only mark paid on verified event. | Guide requirement; automation later. | Webhook signature verified; idempotent. | v2.0 | P3 Normal | API | 14.4 | L | Pending |  | N1
14.6 | 14 SaaS management | Platform dashboard | List tenants with status, plan, last activity, sales count, sync failures. | Operate many customers. | Filter by status works. | v1.2 | P2 Medium | Frontend | 14.1 | M | Pending |  | M5
14.8 | 14 SaaS management | Platform audit and health monitoring | Structured logging (Serilog), /health/ready with DB check, uptime ping, error alerts by email. | Know it is down before customers do. | Alert fires when DB is stopped. | v1.2 | P2 Medium | Ops | 6.13b | M | Pending |  | M5
14.9 | 14 SaaS management | Database backup and restore test | Scheduled pg_dump (daily), keep 14 days, off-machine copy; documented restore into a fresh DB and verified. | Untested backups are not backups. | Restore drill succeeds and sales counts match. | v1.0 | P0 Critical | Ops | 7.17 | M | Pending |  | C6
14.10 | 14 SaaS management | Dedicated installation / licensing process | Document install, license key, update and backup process for self-hosted customers. | Guide: decide before promising offline-only editions. | One-page procedure written. | v2.0 | P4 Low | Docs | 14.4 | M | Pending |  | L1
15.1 | 15 Repeatable run | README: setup and daily run | Prerequisites, creating pos and pos_test databases, user-secrets for JWT key/seed passwords (names only), migrations, run API, run frontend, run tests. | Guide: new developer reliability. | Fresh clone works following only the README. | v1.0 | P1 High | Docs | 11.2 | M | Pending |  | H4
15.2 | 15 Repeatable run | Environment variables reference | Table of every setting (ConnectionStrings__Default, Jwt__*, Seed__*, Cors__Origins, RateLimit__*, VITE_API_URL) with example non-secret values. | Avoids guesswork and leaked secrets. | Every setting used in code is listed. | v1.0 | P1 High | Docs | 15.1 | S | Pending |  | H4
15.3 | 15 Repeatable run | Start script (start-dev.ps1) | PowerShell script: checks PostgreSQL service, applies migrations, starts API and frontend in two windows. | One command to run the app daily. | Script launches both and opens browser. | v1.0 | P3 Normal | Ops | 15.1 | S | Pending |  | N1
15.4 | 15 Repeatable run | Seed demo data | Dev-only seeder for categories, 30 products, opening stock, sample sales. | Quick demos and manual testing. | Seeder only runs in Development. | v1.0 | P2 Medium | API | 8.3 | S | Pending |  | M3
15.5 | 15 Repeatable run | Final runnable checklist | Frontend no console errors, health ok, DB connected, sign-in, product persists, cash sale in history, isolation tests pass. | Guide's verification list. | All items ticked. | v1.0 | P0 Critical | Test | 10.16 | S | Pending |  | C6
15.6 | 15 Repeatable run | Common failures section | Port in use, wrong connection string, migration pending, lockout, CORS, missing env vars - with fixes. | Saves repeated troubleshooting. | At least 8 entries. | v1.0 | P3 Normal | Docs | 15.1 | S | Pending |  | N1
16.1 | 16 Release & operations (added) | Production configuration | Production appsettings, secrets from environment/secret store, HTTPS, forwarded headers, Secure cookies, HSTS. | Local settings are unsafe online. | Checklist passes on staging. | v1.0 | P0 Critical | Ops | 6.13d | M | Pending |  | C6
16.2 | 16 Release & operations (added) | Hosting decision and deployment | Choose host (single VPS with Docker Compose: API, PostgreSQL, Caddy/Nginx for HTTPS, static frontend). Document deploy and rollback. | Needed to give real shops access. | App reachable over HTTPS on a domain. | v1.0 | P0 Critical | Ops | 16.1 | L | Pending |  | C6
16.3 | 16 Release & operations (added) | Database migration process in production | Generate SQL script, take backup, apply, verify; never auto-migrate on startup in production. | Safe schema changes. | Runbook written and rehearsed. | v1.0 | P0 Critical | Ops | 14.9 | S | Pending |  | C6
16.4 | 16 Release & operations (added) | Restricted database user | App connects as non-superuser with CRUD only; migrations use separate owner account; AuthAuditEvents append-only. | Limits damage from a bug or breach. | App user cannot DROP tables. | v1.0 | P1 High | Ops | 16.2 | S | Pending |  | H4
16.5 | 16 Release & operations (added) | Pilot with one real shop | Load real products, run parallel with paper for one week, collect issues list. | Real usage reveals missing basics. | Issue list triaged to v1.1. | v1.0 | P0 Critical | Process | 15.5 | M | Pending |  | C6
16.6 | 16 Release & operations (added) | Kenya compliance review (KRA eTIMS / VAT) | Check whether target customers must issue eTIMS-compliant invoices and what integration is required. | Regulatory requirement may affect receipt design; verify current KRA rules before building. | Written decision: needed / not needed / later. | v2.0 | P1 High | Process | 16.5 | M | Pending |  | H4
16.7 | 16 Release & operations (added) | Swahili/English UI | Translation files, language switch. | Local staff usability. | Cashier screen switches language. | v1.2 | P3 Normal | Frontend | 10.1 | M | Pending |  | N1
16.9 | 16 Release & operations (added) | Basic analytics and exports | Date-range sales, product, stock-valuation reports with CSV export. | Owners ask for exports quickly. | CSV opens correctly in Excel. | v1.2 | P2 Medium | API+Frontend | 9.16 | M | Pending |  | M5

## Versions
Version | Name | Goal | Ships when | Tasks | Critical tasks | Done | % done
v1.0 | Online POS - first usable release | Tenant-safe sign-in, products/categories, cash + M-Pesa-reference checkout, receipts, sales history, stock ledger (receive/adjust), daily report, staff management, backups, deployed and piloted in one shop. | One real shop sells for a week with no data loss; isolation and checkout tests green. | 105 | 63 | 19 | 18.1%
v1.1 | Offline single device + sync | PWA install, local catalogue, offline checkout, safe idempotent sync, conflict flags, CSV product import, discounts, returns. | Sell offline on one device per branch and sync with zero duplicates. | 24 | 0 | 0 | 0%
v1.2 | SaaS operations | Tenant onboarding, plans/trials, manual billing, platform dashboard and MFA, shifts, exports, monitoring, Swahili. | You can onboard and manage several shops without touching the database. | 13 | 0 | 0 | 0%
v2.0 | Scale and compliance | RLS, automated billing, multi-terminal offline, suppliers/POs, variants, images, support sessions, eTIMS review, dedicated installs. | Chosen per customer demand. | 9 | 0 | 0 | 0%
Priority = how important a task is; Version = when it ships. They are independent. Filter Priority = P0 Critical to see what must exist for the app to be safe and correct.
Priority | Meaning | Examples | Tasks | v1.0 | v1.1 | v1.2 | v2.0
P0 Critical | Must be in place. The app is unsafe or wrong without it. | Tenant isolation, sign-in, rate limiting, money maths, checkout, stock ledger, backups | 63 | 63 | 0 | 0 | 0
P1 High | Very important. Needed for real daily use of the shop. | Audit log, daily reports, stock receiving, offline sync, tenant onboarding | 45 | 27 | 14 | 3 | 1
P2 Medium | Important. Makes the app good, but a shop can start without it. | Price-change audit, CSV import, shifts, CI pipeline | 29 | 12 | 10 | 6 | 1
P3 Normal | Can be skipped now and added later. | Password reset by email, Swahili UI, start script | 8 | 3 | 0 | 3 | 2
P4 Low | Can do without. | Product images, customers table, support sessions | 6 | 0 | 0 | 1 | 5

## Requirements
# | Requirement in the guide | Where it is covered | Status | What exists / what is missing | Next action
1 | Tenant, User and TenantMembership with a tenant-specific role | 6.1 to 6.5 | Done | Entities, Identity tables and migration are in place. | None.
2 | Roles: platform administrator, business owner, manager, cashier, stock controller | 6.8, 6.12 | Ready to build | Four tenant roles are seeded. The platform administrator (separate sign-in, scope=platform token, no tenant data access) has full steps and code. | Build 6.12a to 6.12f and pass PlatformAdminTests.
3 | Tenant resolved from the validated authenticated context, never from a browser-sent TenantId | 6.9 | Done | Tenant comes from the signed tid claim. The product create request has no tenant field. | None.
4 | Check permission and membership on every protected operation | 6.10 | Done | Policy handler checks active membership, active tenant and role permission on /products and /me. Sales endpoints do not exist yet. | Apply the same policies to sales endpoints when they are built.
5 | Seed one development tenant and owner account; no hard-coded credentials | 6.8 | Done | Owner and platform admin credentials come from user-secrets. Seeders run in Development only. | None.
6 | Tests that try to reach another tenant's records and expect denial | 6.6, 6.10b | Ready to build | Isolation tests pass (5). The end-to-end authorization tests (6) are written; the test files still have to be added and run. | Add ApiFactory, AuthorizationTests and DbCollection.
7 | Check: users can sign in; a user without membership cannot query a tenant's products or sales | 6.9, 6.10b | Ready to build | Sign-in works. The no-membership test for products is written, not yet run. Sales do not exist yet. | Run the tests; add the sales version when sales endpoints exist.

## Sub-steps
Item | Title | Status | Required by guide? | Notes
6.1 | Domain base types (ITenantOwned, TenantEntity) | Done | Yes
6.2 | Permissions and system role entities | Done | Yes
6.3 | Tenant, TenantMembership and Product entities | Done | Yes
6.4 | Tenant context abstraction and AppUser | Done | Yes
6.5 | AppDbContext: Identity, query filter and SaveChanges tenant rules | Done | Yes
6.6 | Tenant-isolation tests | Done | Yes | 5 tests passing when POS_TEST_CONNECTION is set.
6.7 | Migration AddIdentityAndTenancy | Done | Yes | Applied to pos_dev.
6.8 | Seed roles, demo tenant and owner account | Done | Yes | Credentials from user-secrets.
6.9 | Sign-in endpoint, JWT with sub and tid claims, and /me | Done | Yes | Lockout after 5 failed attempts for 15 minutes.
6.10 | Permission policies, default-deny, product endpoints | Done | Yes | Committed.
6.10b | Add and run ApiFactory, AuthorizationTests and DbCollection | Ready to build | Yes | Needs Microsoft.AspNetCore.Mvc.Testing in Pos.Tests.
6.11 | Refresh tokens with rotation, reuse detection and logout (migration AddRefreshTokens, RefreshTokenTests) | Ready to build | Beyond guide | HttpOnly cookie scoped to /auth, SameSite=Strict, hashed in the database.
6.12a | AppUser.IsPlatformAdmin flag | Ready to build | Yes | Part of migration AddPlatformAdminAndAudit.
6.12b | TokenService: platform token (scope=platform, no tid, 10 minutes) | Ready to build | Yes | Replace TokenService.cs.
6.12c | Platform admin requirement and handler (policy platform.admin) | Ready to build | Yes | Re-checks the database flag and lockout on every call.
6.12d | PlatformAdminSeeder and user-secrets for platform admin | Ready to build | Yes | Never promotes an existing user automatically.
6.12e | Platform endpoints: /platform/auth/login, /platform/tenants, /platform/audit | Ready to build | Yes | Replaces the removed /dev/tenants endpoints.
6.12f | PlatformAdminTests (6 tests) | Ready to build | Yes | Platform admin cannot read tenant products; tenant owner cannot use platform endpoints.
6.13a | AuthAuditEvent entity, DbContext mapping and migration AddPlatformAdminAndAudit | Ready to build | Beyond guide
6.13b | AuditLog service; audit refresh reuse and denial | Ready to build | Beyond guide | A failed audit write never breaks the request.
6.13c | Rate limiting on /auth/login, /auth/refresh and /platform/auth/login | Ready to build | Beyond guide | 10 requests per minute per IP, configurable.
6.13d | Security headers, HSTS outside Development, configurable CORS origins | Ready to build | Beyond guide | Replace Program.cs, AuthEndpoints.cs; add PlatformEndpoints.cs.
6.13e | HardeningTests (5 tests) | Ready to build | Beyond guide | Audit, headers, no-store, CORS, rate limit.
6.14 | Step 6 sign-off: all 28 tests pass, commit, tag step-6-complete | Ready to build | Yes | git tag step-6-complete.
Later | No-membership test for sales endpoints | Pending | Yes | Add when sales endpoints exist.
Later | MFA for the platform administrator | Pending | Before production | Required before any production deployment.
Later | Support sessions: time-limited, audited access to a tenant's data | Pending | Beyond guide
Later | Forwarded headers so rate limiting and audit see the real client IP | Pending | Before production | Needed behind a proxy.
Later | Append-only audit permissions and retention period | Pending | Before production | Restrict UPDATE and DELETE on AuthAuditEvents for the app role.
Later | Cleanup job for expired refresh tokens | Pending | Beyond guide
Later | Frontend sign-in: in-memory access token and automatic refresh | Pending | Beyond guide | Uses credentials: include and refresh on 401.
Later | PostgreSQL Row-Level Security as an extra tenant-isolation layer | Pending | Beyond guide | App role must not own the tables.

## Tests
Test class | What it proves | Expected tests | Status
TenantIsolationTests | Query filter and SaveChanges block cross-tenant reads and writes | 5 | Done
AuthorizationTests | No token, wrong role, no membership and another tenant's record are all denied | 6 | Ready to build
RefreshTokenTests | Cookie hardening, rotation, reuse detection, logout and suspended membership | 6 | Ready to build
PlatformAdminTests | Platform admin separated from tenant data; tenant users cannot use platform endpoints | 6 | Ready to build
HardeningTests | Audit log, security headers, no-store, CORS origins and rate limiting | 5 | Ready to build
| Total expected | 28
| Passing and confirmed | 5